# Campaign Outline: The 100-Kit Challenge

- Campaign Idea & Objective

A 14-day digital donation and awareness campaign aimed at raising funds and in-kind donations to sponsor 100 complete study kits for underprivileged youth. The strategy blends emotional storytelling with direct, functional calls-to-action to drive measurable conversions rather than just vanity metrics.

- Target Audience

-Local community members and young professionals.

- Existing NGO supporters and volunteers.

- Local businesses seeking CSR (Corporate Social Responsibility) opportunities.

- Execution Steps (Phased Approach)

Phase 1: Awareness & Teaser (Days 1-4)

- Launch data-driven graphics highlighting the local literacy resource gap.

- Publish 'Behind the Scenes' reels showing the reality of underfunded classrooms.

Phase 2: Launch & Engagement (Days 5-10)

-Roll out impact stories (carousel posts) featuring past beneficiaries.

- Partner with local digital creators to expand the campaign's organic reach.

- Execute a targeted community hashtag strategy to maximize visibility.

Phase 3: Urgency & Closing (Days 11-14)

- Post daily countdown trackers on Instagram and WhatsApp Stories.

- Share donor shoutouts to build social proof and momentum.

- Final push Reel emphasizing the deadline and immediate impact of a donation.

- Key Messaging & Visual Strategy

The visual aesthetic will prioritize functional, aligned, and professional layouts. By avoiding overly stylized or boxy decorative elements, the campaign ensures that the core message and the CTA remain the undeniable focal point of every deliverable.

- Expected Results & KPIs

-Primary Outcome: 100 study kits fully funded or acquired via direct donation.

- Reach & Engagement KPI: 40% increase in profile visits and an engaged follower growth of 15%.

- Retention KPI: 50 new email sign-ups added to the volunteer database for future marketing initiatives